## Slide 1: ALE HR 2026 Plan Review & Feedback
Prepared by HR Business Partner (Glencore)
29 June 2026

## Slide 2: Overall Assessment
Larissa's 2026 HR Plan is ambitious and covers critical areas.
This review provides:
  Structured feedback on each of the 4 key initiatives
  Identification of MoOC (Management of Operational Change) requirements
  Observations on TSA compliance alignment
  Recommendations for sequencing and risk mitigation

## Slide 3: 1. Organizational Design (MoOC Required)
Revise and implement new organizational model with clear roles and strategic alignment
Weight: 20%
Feedback:
  Requires full MoOC process per TSA Section 13.1
  Plan lacks specifics on scope: which BUs/departments?
  Cross-BU impact requires CEO Recommend + BoD Decide
  Headcount variations >5% require CEO sign-off
  Missing: Timeline, phasing plan, and budget impact estimate
  Competency Assessment Framework KPI is good but needs detailed milestones

## Slide 4: 2. Pay Equity & Risk Mitigation (MoOC Required)
Implement governance structure for pay equity; mitigate labor and reputational risks
Weight: 20%
Feedback:
  Good: Phased approach acknowledged given budget constraints
  Correctly identifies need for legal advice + RemCo approval path
  Per TSA Section 13.3: Salary structure changes require BoD decision
  Salary Benchmarking (Taiane) must be completed BEFORE corrections can be designed
  Missing: Budget estimate for corrections, legal risk quantification, timeline per phase
  Missing: Phased prioritization criteria (by risk level? department size? cost?)
  Brazilian Lei 14.611/2023 (equal pay) carries fines up to 3% of payroll

## Slide 5: 3. Cultural Transformation (MoOC Recommended)
Execute ALE's Cultural Transformation - Accountability Mindset
Weight: 20% | Timeline: Q2 2026 leadership alignment, continuing 2027/28
Feedback:
  Good alignment with HSEC and Human Rights Strategy (2027/28)
  Q2 2026 deadline for leadership engagement has likely passed - need status update
  'Accountability Mindset' needs a clear definition document with observable behaviors
  Missing: How will culture change be measured? Surveys? Behavioral indicators?
  Missing: Communication strategy, training program, performance management integration
  Risk: If perceived as punitive rather than empowering, could suppress safety reporting

## Slide 6: 4. HR Governance & Process Excellence (MoOC Required)
Implement HR governance model: standardization, compliance, digitalization, efficiency
Weight: 20%
Feedback:
  Critical initiative - directly supports TSA compliance
  Needs to specify which HR processes are being standardized and current gaps
  Digitalization ties to HR Systems Assessment - must be coordinated
  If payroll is outsourced, requires separate MoOC for data security & continuity
  This initiative underpins ALL others - standardized processes are prerequisite

## Slide 7: Supporting Projects - Feedback
Salary Benchmarking
  Status: Taiane to define scope - this is a dependency for Pay Equity
  Recommend external market data provider (Mercer/WTW/Korn Ferry for Brazil)
HR Systems Assessment
  Payroll replacement/outsourcing + PMS assessment and selection
  Requires business case with cost-benefit analysis before proceeding
Performance Management
  Link to Competency Assessment Framework from Org Design initiative
  Timeline unclear - is this H1 or H2 2026?

## Slide 8: MoOC Requirements Summary
Initiative | MoOC Required? | Priority | Document
Organizational Design | Yes - Mandatory | High | 01_MoOC_Organizational_Design
Pay Equity & Risk Mitigation | Yes - Recommended | High | 02_MoOC_Pay_Equity
Cultural Transformation | Recommended | Medium | 03_MoOC_Cultural_Transformation
HR Governance Model | Yes - Mandatory | High | 04_MoOC_HR_Governance_Model

## Slide 9: Key Risks Identified
1. TSA Compliance
  Several initiatives touch TSA authority matrix areas. Without proper MoOC documentation and approvals, ALE risks non-compliance.
2. Sequencing Dependencies
  Salary Benchmarking must precede Pay Equity; HR Systems must align with HR Governance. A master timeline is needed.
3. Budget Competition
  Multiple initiatives competing for limited budget. Prioritization framework needed.
4. Capacity
  Team capacity to execute all initiatives simultaneously is unclear.